Definitions for “Research” and "Technical Enrichment”

Research:  An important and necessary endeavor that aimed at studying specific code related issue(s)/topics for the purpose of providing solutions to a specific problem or future code change(s) directed at improving the implementation and enforcement of the FBC.  The issue to be researched must be fully understood (i.e. with clear purpose of doing the research/goals); clearly defined with specific scope of work/approach; and within budget.

Technical Enrichment: An important and necessary endeavor that is aimed at evaluating complex related code issue(s)/topics for the purpose of providing educational/clarification experience or alternative solutions directed at improving the implementation and enforcement of the FBC.  Method of delivery for these matters is through workshop/TAC meetings with specific participation of expert(s) in subject area of concern.

Research Work plan

April - July 2020 		Solicit research topics

July 2020	Compile research topics submitted and make available list of research topics for review at the August 3, 2020 HRAC meeting

August 3, 2020	HRAC meeting to consider and recommend list of research topics for consideration by the Commission

August 4, 2020	Commission discusses and consider recommended list of research topics

August /Sept. 2020   	Solicit qualified entity to do the research

October 2020	Draft contract for research and implementation

November 2020  		Start contract (contract time frame 1- year)

Funding is contingent upon budget appropriation and must be spend within the Fiscal year.

June 15, 2021		Complete research or partial research