Tasks re-ordered and renumbered December 2009

### FLORIDA BUILDING COMMISSION 2009 WORKPLAN

Note: Red type indicates task originated as requirement of a law.

ANNUAL ADMINISTRATIVE TASKS

1.	Report to 2010 Legislature

Schedule:

Commission identifies and receives draft recommendations				12/12/09

Commission report to 2009 Legislature						2/10

Status:		Pending

% Complete

100%

Origination:	Commission. Annual task authorized by statute

2.	 Workplan Prioritization

Schedule:

Survey sent to Commissioners							11/09

Review results at meeting								12/09

Status:		Pending

% Complete

0%

Origination:	Commission. Annual task.

3.	2010 Commission Effectiveness Assessment Survey

Schedule:

Discussion of survey instrument at Commission meeting				2/10

Review results at meeting								4/10

Status:		Pending

% Complete

0 %

Origination:	Commission. Annual task.

2010 FBC UPDATE DEVELOPMENT TASKS

Code Assembly Process

4.	Evaluate and Adopt the Development Process for the 2010 Florida Building Code

Schedule:

Chairman appoints a study committee						1/08

Committee meets to review and develop recommendation on 2010 FBC 		12/10/08

compilation approach

Committee expanded to consider code development proceedings and schedule	4/7/09

and declaratory statements process

Committee meetings									6/8/09

Commission conducts public hearing	and adopts plan				10/09

Status:		Pending

% Complete

75%

Origination:	Chairman and Staff planning for the 2010 FBC development.

5.	2010 Update to the Florida Building Code

Schedule:

Printed 2009 International Codes published and available to the public		4/2/09

2009 I Codes must be available to public for 6 months prior to selection

Commission selects 2009 I Codes as foundation for 2010 FBC (Oct Cmsn meeting)		10/13/09

Staff evaluates changes of 2006 to 2009 I Codes for overlap with Florida amendments	4/09-11/09

TACs review existing Florida amendments that overlap with 2006 to 2009 I code		12/6-9/09

changes and develop recommendations for retaining the Florida amendment

or the new I code requirement.  (see subtask below)

All existing Florida amendments compiled in 2009 I Codes format posted to website	2/1/10

including TAC recommendations for “overlapping” amendments

Note: Proposed amendments to existing “Florida specific” code requirements must be made to the section numbers provided in this document. Staff will not correlate proposals for proponents.

Local amendments posted to the website							2/1/10

FFPC to FBC correlations/overlaps identified and recommendations developed 		1/20/10

(see subtask below)

Submittal of new proposed amendments for the 2010 FBC opens				3/1/10

New proposed amendments for the 2010 FBC due and process closes			4/2/10

Proposed amendments reviewed by staff and posted to the Commission website 		5/1/10

45 day comment period ends	(By law- 45 day min before TAC review)				6/15/10

TACs review proposed Florida amendments and make recommendations			8/9-10/10

at Rule Development Workshop(August 2010 Commission meeting)

TAC recommendations posted to the website						9/3/10

45 day comment period ends	(By law- 45 day min before Commission review)			10/18/10

TACs review comments on their recommendations and prepare public comment		11/15/10

for the Rule Hearing

Commission considers TAC recommendations on proposed amendments			12/7-8/10

at the Rule Adoption Hearing	(December 2010 Commission meeting)

File the Rule adopting the 2010 FBC	and post the Supplement on the website		2/1/11

2010 Florida Building Code Rule is final but with implementation date of 12/31/11	3/1/11

(By law- Code must be available for 6 months before implementation)

Code amended to resolve glitches (see Glitch schedule below) 					4/11-6/11

Code printed with integrated Florida modifications and glitch fixes				10/1/11

Code implemented										12/31/11

Note: By law this is the latest date the Florida Fire Code can be implemented.

The goal is to implement the FFPC and FBC concurrently.

Subtasks:

Review Florida specific amendments that overlap with 2006 to 2009 I Codes changes	12/09

(Note: Law requires review of Florida specific amendments when I codes changes address the Florida

amendment issue. The Commission must decide whether to retain the Florida amendment or to adopt

the I code requirement. All other Florida specific amendments roll forward into the FBC update unless modified

or removed by an approved amendment proposal. Staff will identify overlaps for the TACs’ and Commission’s

consideration and decision.)

Joint Fire TAC/Fire Code Advisory Council review of I Codes/NFPA 1/NFPA 101	1/10

changes for overlaps/conflicts

Contractor reviews Building and Fire codes and reports				1/10

Joint Fire TAC/FCAC meeting to develop recommended fixes			1/20/10

Recommended correlation fixes posted to the web					2/1/10

Fire TAC reviews proposed building code amendments for fixes			8/9-10/10

(Note: Law requires the Commission and State Fire Marshal to maintain the FBC and FFPC

for consistency to avoid conflicting requirements. A contractor will identify new overlaps resulting

from changes in the new editions of the I codes and NFPA codes for consideration by the joint Fire TAC

and Fire Code Advisory Council and decision on FBC amendments  by the Commission)

(Note: Subtasks identify proposed code modifications that are integrated into the code development process.)

Status:		Pending

% Complete

5%

Origination:	Requirement of law that the Commission updates the Code triennially..

# 6.	Glitch Amendments to the 2010 Florida Building Code

Schedule:

2010 FBC Supplement published online							2/1/11

Glitch amendment submittal DEADLINE							3/1/11

(Note: The Code publisher will identify correlation glitches and unintended consequences of Florida

specific amendments in the final 2010 FBC Supplement for correction by glitch amendment. See subtask

for adoption of the 2011 NEC via the glitch proceeding)

Rule development workshop	(April Commission meeting)					4/5/11

Rule adoption hearing	  (June Commission meeting)						6/7/11

Glitch Rule adopted (filed)									7/1/11

Code printed with first cycle glitch fixes and available to the public				9/1/11

2010 FBC effective										12/31/11

Note: By law this is the latest date the Florida Fire Prevention Code can be implemented.

The goal is to implement the FFPC and FBC concurrently.

Subtasks:

Review 2011 NEC (Note: not subject to glitch proposal submittal deadline)		1/11-2/11

Proposal to adopt 2011 NEC submittal deadline						3/1/11

Recommend whether to adopt as glitch  (August Commission meeting)				4/5/11

Adoption per schedule above

Joint Fire TAC/Fire Code Advisory Council review of I Codes/NFPA 1/NFPA 101	2/11

Status:		Pending

% Complete

0%

Origination:	Requirement of law that the Commission updates the Code triennially..

ENERGY CODE TASKS

The 2008 Legislature established several directions for development of the Florida Energy Code provisions of the 2010 Florida Building Code. The broadest direction is the requirement for 20% increase in efficiency and the other tasks fall under it. Three additional not legislated energy code related tasks are on the work plan also. All tasks must be coordinated for determination of the requirements for the 2010 Code. Consequently, they are organized under the broad task.

Primary Task -

7.	Study Energy Conservation Measures Code Compliance Methods and Develop a Plan for Increased Efficiency Requirements for Future FBC’s (HB 697 and HB 7135)

Origination:	The 2008 Legislature directed the Commission to enact specific increase in building energy efficiency requirements in HB 697 (Building Code) and HB 7135 (Energy). This task initiates the study and development of a schedule of increasing requirements, the first of which are to be enacted in the 2010 FBC whose development begins in 2009.

Sub-Tasks –

7a.	Develop Rule for Energy Code Cost Effectiveness Test (HB 687 and HB 7135)

Schedule for Sub-Task 27:

Appoint Work Group									12/9/08

Work Group/TAC meetings to develop recommendation				2/3/09

3/5/09

3/27/09

Rule Development Workshop								4/09

Rule Adoption Hearing								6/09

Notice of Change published								7/3/09

Rule Effective										9/1/09

Status:		Complete

% Complete

100%

Origination:	The Commission was directed by the 2008 Florida Legislature in HB 697 and HB 7135 to develop a cost effectiveness test criteria by rule to be applied to justification for increased residential building energy efficiency requirements.

7b.	Study Energy Conservation Measures for Replacement of Air Conditioning Equipment

Origination:	Recommendation of the Energy TAC resulting from consideration of Energy Code amendment proposals regarding replacement air-conditioning systems at the October 2008 meeting. Approved by the Commission October 15,2008.

Schedule:

Work Group/TAC considers options and develops consensus plan			3/27/09

4/30/09

Recommendation adopted						5/28/09

Proposals for 2010 FBC submitted for adoption					3/10

(See 2010 FBC development schedule)

Status:		In progress

% Complete

75%

7c.	Develop Strategic Plan for Energy Standards Revision Pursuant to s.553.9061, F.S.

Subtask 46

Schedule:

Workgroup appointed									12/9/08

Workgroup meetings									4/30/09

5/28/09

8/11/09

9/3/09

Recommendation Adopted						10/14/10

11/12/09

Recommendation to Commission							12/09

Status:		In Progress

% Complete

100%

Origination:	The 2008 Legislature directed the Commission to enact specific increases in building energy efficiency requirements in HB 697 (Building Code) and HB 7135 (Energy). This sub- task initiates the study and development of a schedule.

7d.	Develop Recommendations for 20% Increased Energy Efficiency Requirement for 2010 FBC (HB 697 and HB 7135)

This task integrates the outputs of Task 35 and the Sub-tasks to develop a draft of Energy Code chapters for the 2010 FBC.

Schedule:

Workgroup appointed									12/9/08 Commission approves output of Task 27 and adopts requisite Rule			6/9/09 Workgroup adopts strategic plan for Commission approval				10/12/09 Contractor and Workgroup develop draft 2010 Energy chapters			9/09 -12/09    Proposals for 2010 FBC submitted for adoption					3/09

Status:		Pending

% Complete

20%

Origination:	In addition to the directives indicated in Task 35 and sub-tasks, the 2008 Legislature amended the building code law to require the IECC be adopted as a foundation code to be amended not less stringent than the Florida Energy Efficiency Code for Building Construction. The building code law requires updating the Code every three years with the 2010 FBC the next edition.

7e.	Identify Specific Building Options to Achieve the Energy Efficiency Improvements (list identified in HB 697 and HB 7135)

Schedule:

To be conducted as part of 2010 FEC recommendations development Task 47

Origination:	Energy act of 2008 (HB 7135) directs the Commission to include, as a minimum, certain technologies for achieving enhanced building efficiency targets established by the Act in the Florida Energy Code. The Building Code act of 2008 (HB 697) directs the Commission to facilitate and promote the use of certain renewable energy technologies.

7f.	Investigate Humidity Control Problems for Hot and Humid Climates

Schedule: 	In Progress

To be conducted throughout the project

Orgination: The original workgroup recommended not pursuing special ratings for AC equipment used in hot and humid climates and recommended addressing the concerns with matching equipment moisture removal capabilities to building latent and sensible heat loads through the Florida Energy Code. Potential moisture control problems will be a part of the consideration for how to achieve improved building energy efficiencies directed by law.

Status: for Sub-Tasks 42 & 26:		Pending

% Complete

20%

7g.	Develop Criteria for Energy Efficient Pool and Spa Systems

Subtask 29

Schedule:

Pool Sub-workgroup appointed							4/8/09

Workgroup meetings									6/8/09

8/12/09

2/3/10

Proposals for 2010 FBC submitted for adoption					3/10

(See 2010 FBC development schedule)

Status:		Pending

% Complete

50%

Origination:	Energy act of 2008 (HB 7135) directs adoption of pool pump efficiencies in the 2010 FBC. During discussions with the Florida Spa and Pool Association regarding energy efficiency requirements for pool pumps members suggested improved efficiency could be achieved through criteria for pool hydronic system design.

7h.	Evaluate Requirements for Green Roofs Recognition in Florida Building Code

Subtask 45

Schedule:

Cool Roofs Workgroup appointed							4/8/09

Workgroup meeting									2/2/10

Proposals for 2010 FBC submitted for adoption					3/10

(See 2010 FBC development schedule)

Status:		Pending

% Complete

10%

Origination:	Energy act of 2008 (HB 7135) directs the Commission to include, as a minimum, certain technologies for achieving enhanced building efficiency targets established by the Act in the Florida Energy Code. Energy efficient roofs are one category. The Building Code act of 2008 (HB 697) directs the Commission to facilitate and promote the use of certain renewable energy technologies.

The Roofing TAC requested a special committee to address green roofs at the December 2008 Commission meeting.

ACCESSIBILITY CODE UPDATE

8.	Develop Integration of Florida Accessibility Law into the 20?? Standards for Accessible Design Being Adopted by the US Department of Justice

Schedule:

Appoint work group									12/12/08

Staff Developed Starting Draft							1/09

Meetings										2/2/09

4/6/09

6/9/09

8/10/09

10/12/09

12/7/09

Recommendation to Commission							2010

Public Hearings									2010

Commission adopts recommendation to Governor and Legislature			2010

Report to Legislature									2011

Status:		Pending

% Complete

40%

Origination:	Recommended by Access TAC and approved by Commission at October 2008 meeting.

GENERAL  TASKS

9.	Investigate a Consistent Definition of “Bedroom” for Department of Health On-site Septic System Sizing Regulations

Schedule:

Appoint a Commission Ad Hoc committee						3/19/08

DOH appoint members to work with Commission Ad Hoc committee		3/08-4/08

Task group meetings									5/7/08

10/15/08

4/7/09

DOH TRAP meets 									Summer 09

Report to Commission and DOH							10/09

Commission considers report and recommendation to Legislature			12/9/09

Additional consideration by TRAP							1/10

Status:		In Progress

% Complete

88%

Origination:	The initiative to develop consistency between building department and health department judgments of the number of bedrooms in a home as it applies to onsite sewage treatment system sizing was suggested by Commissioner Browdy for two legislative sessions and the joint project with Department of Health was established by mutual agreement during the 2007 Legislative Session.

10.	Develop Criteria for Evaluation Entity Approval and Adopt by Rule or Develop Recommendation for 2009 Legislature for Entities to be Recognized in Law

Schedule:

Product Approval POC considers at meetings					8/08-12/08

Recommendation to Commission for vote						12/10/08

Option 1:  Selected

Recommend adding entities to list in law

Commission includes in report to Legislature (See Task 36)		2/09

Status:		Completed – Commission recommendation was in bill that died

% Complete

100%

Commission decides to implement option 2						6/9/09

Option 2: Recognize IAPMO by Rule

Rule Development Workshop by conference call					7/20/09

Rule Adoption Hearing by conference call						9/09

Rule effective										10/09

Commission considers recommendation to 2010 Legislature			12/9/09

Status:		Working second option provided by law

% Complete

90%

Origination:	The 2008 Legislature directed the Commission to review the list of Product Evaluation Entities currently identified in law and either recommend modifications to the list or establish criteria for approval of additional entities by rule and report on those criteria to the 2009 Legislature.

11.	Evaluate Swimming Pool Entrapment Standards Application to Existing Pools

Schedule:

Appoint Subcommittee to the Plumbing TAC					4/8/09

Workgroup meetings									6/8/09														8/12/09

Declaratory Statement request to clarify current code				12/09

Commission considers any legislative recommendation				12/09

Status:		Pending

% Complete

40%

Origination:	Plumbing TAC recommendation approved by Commission June 2008. Proposed by Spa and Pool association.

12.	Coordination with Florida Department of Health on Accessible Restroom Requirements in Public Pool Licensing Regulations

Project Deferred to 2010 FBC Development Process

Schedule:

Staff Meetings										2/10

DOH submits proposed rule changes							4/10

2010 FBC development proceeding	(see schedule)					12/09-12/10

Status:		Pending

% Complete

20%

Origination:	Commissioner Norkunas’ recommendation to the Commission approved at the June 2008 meeting.

13.	Evaluation of Standards to Address Corrosive Gypsum Board Outgassing

Schedule:

DOH led Committee appointed							2/09

Meetings										4/09-9/09

Note: DOH project discontinued no directive to the Commission for action. Defer to the 2010 FBC development.

Recommendation to Commission

DOH rule amendment and 2010 FBC submitted by	(DOH preliminary determination is no health hazard so no rule will be pursued for now.)

Status:		Pending

% Complete

30%

Origination:	State Incident Action Plan assignment resulting from the state emergency management mobilization to address “Chinese Drywall”.

HURRICANE RESPONSE RELATED TASKS

14.	Load Side - Wind Pressure Research

Schedule:

Commission approved redirection of WBD project Phase II				3/07

Amend contract with UF/ARA							4/07

Contract for Phase III									9/07

Progress reporting									9/30/07

12/10/07

1/30/08

Report on Phase III	(Note: August 2008 mtng canceled due to TS Fay)		10/08 & 12/08

Continued support of hurricane wind testing						indefinite

Status:		Substantially Complete

% Complete

95%

Origination:	Hurricane Research Advisory Committee identified design pressure requirement errors while conducting wind tunnel testing for the Panhandle wind-borne debris projected directed by the Legislature. Subsequent research was conducted to provide the base of improved roof edge design pressure requirements.

15.	Resistance Side – Component and Cladding & MWFRS Research

Schedule:

Legislature appropriates funding							5/07

Contract with UF to conduct research						9/07

(Includes post hurricane building damage assessment survey contingency)

HRAC develops research priority list							1/08

Report on Phase III									10/08 & 12/08

Contract extension for additional testing						1/09

Reporting										4/09

Reporting at HRAC									10/09

HRAC recommendation for continuation of projects					12/09

Continued support of window/wall, soffit and other building component testing	indefinite

Status:		In Progress

% Complete

50%

Origination:	Hurricane Research Advisory Committee identified building failures in 2004 and 2005 hurricanes, recommended quick-fixes for some and identified areas needing further research before standards are established. The Commission sought funding and research work was initiated in 2007.

16.	Evaluate Hurricane Wind Pressure and Wind Driven Rain Criteria for Soffit Systems and Establish Labeling Requirements

Schedule:

Appoint workgroup									3/19/08

Include task in UF components and cladding contract				3/08

Workgroup meetings									11/6/08

2/4/09

4/8/09

7/09-9/09

Recommendations ready to propose for 2010 FBC					2/10

Report to Structural TAC and Commission						2/10/10

Additional requirements pursued through 2010 FBC development proceeding

Status:		Pending

% Complete

50%

Origination:	Soffit manufacturers requested formation of a work group to develop label  requirements similar to the Commission’s action for windows, shutters and garage doors then expanded the request to include developing installation requirements. Investigation of performance and development of the basis for installation requirements is one of the elements of the components and cladding research being conducted under Task 15.

17.	Develop Criteria for Use of Gravel Roof Systems

Schedule:	RECOMMEND DELAY DUE TO BUDGET CONSTRAINTS

Appoint Workgroup									2/09

Workgroup meetings									4/09

6/09

8/09

Recommendations for 2010 FBC for Commission review				10/09

Proposals for 2010 FBC submitted							12/09

Status:		Pending

% Complete

0%

Origination:	During the evaluation of whether gravel roof systems should be prohibited by the 2007 FBC, Task 19, the Florida Roofing and Sheet Metal Association and Commission agreed to retain gravel roof systems and apply the HVHZ criteria throughout the state initially then develop improvements to the systems.

18.	Evaluate Adoption of Flood Standards in the Florida Building Code

Schedule:

Workgroup appointed									12/08

DEM contract with FSU/CRC							1/09

Workgroup meetings									3/25/09

4/29/09

5/29/09

Review companion local ordinance and local variance authority issue	1/13/10

Recommendations to Structural TAC & Commission				8/11/09

Proposals for 2010 FBC submitted for adoption					3/10

(See 2010 FBC development schedule)

Status:		Pending

% Complete

88%

Origination:	The Florida Division of Emergency Management and FEMA requested the policy established in 2000 regarding flood requirements adoption outside the building code be reviewed. DEM will provide a grant to fund the project.

19.	Evaluate Resolution of CCCL and V Zone Requirement Inconsistencies

Schedule:	Future project. Funds are limited in FY 2009-2010.

Status:		Pending Approval of Flood Standards Workgroup Recommendation

% Complete

Origination:	The Flood Standards Workgroup’s report recommended this issue be addressed by a separate workgroup for resolution.

20.	Evaluate Storefront and Curtain Wall Glazing Labeling for the 2010 Florida Building Code

Schedule:

Workgroup appointed									2/09

Workgroup meetings									6/15/09

Recommendations to Commission							12/09

Proposals for 2010 FBC submitted for adoption					3/10

(See 2010 FBC development schedule)

Status:		Pending

% Complete

5%

Origination:	Industry request at the December 2008 Commission meeting.

OTHER ENERGY AND GREEN TECHNOLOGY TASKS

Green Technologies

Water Conservation Initiatives

21.	Evaluate Rainwater Collection and Reuse for Process Water and Other “Green” Technologies in Coordination with DOH, Health Officials, DEP and Other Water Management Agencies

Origination:	Plumbing TAC recommendation approved by Commission June 2008. Also, of special note is the 2008 Energy Act (HB 7153) establishes water conservation policies that parallel energy conservation policies, some of which were assigned to the Commission. The building code law directs the Commission to address new technologies in the codes and the field of “green technologies” is advancing rapidly. Standards essential to the development and recognition of safe products and systems are a responsibility of the Commission.

Schedule:	RECOMMEND DELAY DUE TO BUDGET CONSTRAINTS

22.	Evaluate in-home waste water recycling in coordination with Department of Health and Department of Environmental Protection (Previous Task 14)

Origination:	This task was originated based on overtures by the Florida Department of Health and Florida Department of Environmental Protection. It was first addressed  for the 2007 FBC and resulted in the inclusion of the Florida Department of Health requirements for within home grey water capture and reuse for irrigation outside homes. Reuse inside homes was not completely addressed.

Schedule:	RECOMMEND DELAY DUE TO BUDGET CONSTRAINTS

Appoint Workgroup									2/09

Workgroup meetings									4/09

6/09

8/09

Recommendations for 2010 FBC for Commission review				10/09

Proposals for 2010 FBC submitted							12/09

Status:		Pending

% Complete

5%

TASKS COMPLETED IN 2009

Note: Task numbering listed below are from 2008-09 workplan.

2007 FBC AND GLITCH AMENDMENT RELATED TASKS

# 2.	Glitch Amendments to the 2007 Florida Building Code (Previous Task 8.)

Schedule:

2007 Code published online								2/1/08

Printed 2007 Codes available to the public						3/1/08

Glitch amendment submittal DEADLINE						7/15/08

Rule development workshop								10/15/08

Rule adoption hearing									12/10/08

Glitch Rule effective									3/1/09

2007 FBC effective									3/1/09

Status:		Completed

% Complete

100%

Origination:	Commission. Triennial task subsequent to FBC Update authorized by statute

14.	Amend the Florida Energy Code to Require 15% More Efficiency in Buildings (Previous Task 37)

Schedule:

Note: Amendment to achieve Governor Crist’s directive of 15% increased efficiency by January 1, 2009 will be done using procedures of Part VI, chapter 553, F.S. The Energy Code will be amended by administrative rule authorized by that part then the revised Energy Code will be adopted into the 2007 Florida Building Code during the currently scheduled “glitch” cycle.

Evaluation of cost effective building component efficiencies completed		1/08

(See Task 13)

Department of Community Affairs recommendations to the Commission		1/08

Commission considers proposed amendments					1/08-2/08

Rule Development Workshop								3/19/08

Rule Adoption Hearing								5/7/08

Supplemental Rule Adoption Hearing						10/15/08

Rule filed										7/08

Adoption into 2007 FBC via “Glitch” cycle (See Task 2)

Status:		Completed

% Complete

100%

Origination:	The Governor directed the Commission to amend the Florida Energy Code to increase requirements for building energy efficiency by 15% in Executive Order 2007-127.

16.	Work with DCA to evaluate updated energy efficiency standards for energy using products (Previous Task 25 & 38)

Schedule:

DCA initiates rule proceeding							8/07

Enter into contract for study								9/07

DCA Secretary Pelham addresses Commission suggesting coordination		10/3/08

DCA conducts Rule Development Workshop					10/18/07

Report from contractor								11/07

Recommendations finalized for report to 2008 Legislature				1/30/08

Report to 2008 Governor								2/08

Update efficiency standards in Florida Energy Code					5/7/08

Status:	Commission denied DCA proposals for increasing appliance/systems energy efficiency in the Florida Energy Code update.

% Complete

0%

Origination:	The Governor directed the Department of Community Affairs to amend the Florida Appliance Efficiencies to increase energy efficiency requirements by 15% in Executive Order 2007-127. DCA Secretary Pelham addressed the Commission and requested its cooperation in complying with the directives of the Governor’s EO. DCA/Commission staff presented a plan for increasing efficiency requirements for appliances and energy using equipment that fall within the authorities of the Florida Energy Code. The Commission rejected the proposed amendments at its May 2008 meeting thereby not providing the coordination and cooperation requested by DCA.

17.	Develop mitigation techniques for retrofit of existing site-built residential buildings: (Previous Task 27)

Schedule:

Identify techniques for initial adoption						5/07-6/07

Commission initiates rule development for techniques & retrofit mandates		5/09/07

Rule development workshop								6/27/07

Non-rule workshop									8/8/07

Rule adoption hearing									8/22/07

Rule effective										10/10/07

Appoint Workgroup to refine requirements						10/3/07

Workgroup meets to recommend settlement for FRSA rule challenge		10/3/07

Commission holds telephone meeting to consider settlement			1/8/08

Workgroup meetings to refine mitigation techniques for Glitch Cycle		12/13/07

1/28/08

3/19/08

4/18/08

Submit for amendment of 2007 FBC during Glitch Cycle				5/08

Adopt techniques and retrofit mandates in 2007 FBC via Glitch Cycle

See Glitch Amendment Task 8 schedule

Status:		Completed

% Complete

100%

Origination:	Development of mitigation techniques and adoption as Code requirements as directed by the law was directed by the 2007 Florida Legislature in CS/HB 7057.

18.	Electrical bonding and grounding for swimming pool decks (Previous Task 28)

Schedule:

Notify building departments/pool bonding alternative authorized by law		5/07

Develop alternative technique to NEC						5/07-6/07

Commission initiates rule authorizing alternative technique				5/09/07

Rule development workshop								6/27/07

Adopt the alternative in the 2007 FBC						8/22/07

Rule effective	 									10/1/07

Adopt alternative technique in 2007 FBC via Glitch Amendment Cycle		2008

See Glitch Amendment Task 8 schedule

Status:		Completed

% Complete

100%

Origination:	The 2007 Florida Legislature directed adoption of the alternative pool bonding requirements by non-Code rule in 2007 and adoption in the 2007 FBC in CS/CS/SB 2836.

19.	Evaluate elimination of gravel and stone roofing systems (Previous Task 29)

Schedule:

Appoint Ad Hoc committee to evaluate the science, alternatives,			8/07

business impact and impact on birds

Contract with UF to provide technical assistance					9/07

Workgroup meetings to review data UF reports on literature search			12/10/07

1/08

3/08

4/18/08

5/6/08

Submit for amendment of 2007 FBC during Glitch Cycle				5/08

Amend 2007 FBC as determined by study in Glitch Cycle		      See Task 8

Status:		Completed

% Complete

100%

Origination:	The 2007 Florida Legislature directed the Commission to evaluate the consequences of adopting the International Building and Residential Codes prohibition of gravel roof systems in high wind areas before adopting it into the 2007 FBC and to take remedial action if warranted.

20.	Implement requirements of law for carbon monoxide detectors (Previous Task 32)

Schedule:

Commission initiates special rule development and adoption for			5/9/07

buildings with fuel burning appliances, fireplaces or attached

garages and sleeping rooms

Rule development workshop								6/27/07

Mechanical and Electrical TACs decide how to reference from NEC		8/21/07

Rule adoption hearing									8/22/07

Rule effective	(date set by law)							7/1/08

Adopt and implement above requirements in 2007 FBC in Glitch Cycle		2008

and DBPR hotels with fuel fired boiler requirements DBPR did not adopt a rule

See Glitch Amendment Task 8 schedule

Status:		Completed

% Complete

100%

Origination:	The 2007 Florida Legislature directed the Commission to adopt carbon monoxide detector requirements written into law as a separate non-Code rule to take effect July 1, 2008 and to adopt the requirements in law into the 2007 FBC.

28.	Develop Legislative Recommendation for Building Code Carbon Monoxide Detector

Requirements

Schedule:

Mechanical TAC considers								10/13/08

Expand review to a workgroup to include additional stakeholder groups		10/15/08

Recommendations to Commission 							12/08

Report to 2009 Legislature								2/09

Status:		Completed

% Complete

100%

Origination:	Commissioner Bassett advised the Commission that the 2007 Law requirements  for carbon monoxide detectors would not provide effective safety for facilities with boilers. Inquires were made by staff during the 2008 Legislative Session regarding delegating establishment of criteria to the Commission by rule. The response was the Commission should work on criteria that could be changed in law.

32.	Design Charette for Hotel Room Accessibility

Schedule:

Charette planning									1/08-10/08

Conducted during December 2008 Commission meeting				12/08

Status:		Completed

% Complete

100%

Origination:	Accessibility TAC

36.	Evaluate Need for 4 Hour Bldg Code Core Course as Licensing Requirement

Schedule:

POC conducts workshops								08/08-12/08

Recommendation to Commission							12/12/08

Commission finalizes recommendations for Report					1/30/09

Commission report to 2008 Legislature						2/09

Status:		Completed

% Complete

100%

Origination:	Education POC. Voted approved by Commission at June 24, 2008 meeting.

37.	Evaluate Amending 9B-72.180 on Equivalency of ASTM E 1300-02 and ASTM E 1300-04 and Rule 9B-72.090 on Product Approval Self Affirmation

Schedule:

Structural TAC Recommendation on Equivalency to Commission			10/15/08

Rule Development Workshops							12/10/08

Rule Adoption Hearings								2/04/09

Rule Effective										3/09

Status:		Completed

% Complete

100%

Origination:	Product Approval POC. Voted approved by Commission at June 24, 2008 meeting.

41.	Review the 2008 National Electric Code for Adoption by Separate 2009 Glitch Amendment

Schedule:

Electrical TAC review meetings							12/9/08

2/3/09

Rule development workshop								4/8/09

Rule adoption hearing									6/9/09

Effective										7/09

Status:		Completed

% Complete

100%

Origination:	Recommended by Electrical TAC and approved by Commission at October 2008 meeting.

42.	Repeal of CO Detector, Pool Bonding and Mitigation Rules

Schedule:

Rule Hearing										2/3/09

Effective										3/1/09

Status:		Completed

% Complete

100%

Origination:	Housekeeping. Directed by law to adopt rules to govern until the 2007 FBC takes effect. Requirements integrated into the Code via glitch amendment cycle. Original rules are redundant and must be repealed to eliminate potential conflicts.

51.	Evaluate Equivalence of 2009 Florida Energy Code Commercial Building Requirements to ASHRAE 90.1-2004 and Certify to the U.S. Department of Energy

Schedule:

Evaluation conducted by staff/contractor						3/09-8/09

TAC considers evaluation report							10/09

Recommendations to Commission							10/13/09

Commission reports to Governor’s Office and DOE					10/09

Status:		Complete

% Complete

100%

Origination:	This task is required by federal law. Title III of the Energy Conservation and Production Act, as amended, (42 U.S.C. 6833(b)(2)(B)(i))requires that each state must certify equivalence of its energy code to the edition of ASHRAE 90.1 that the U.S. Department of Energy determines sets the energy efficiency standard for commercial buildings.

| WORKPLAN PRIORITIZATION EXERCISE RESULTS CONDUCTED OCTOBER 15, 2008 |
| --- |
| WORKPLAN TASK | OVERALL RANKING |
| 39.) Energy conservation measures | 1 |
| 1.) Report to 2009 Legislature | 2 |
| 22.) 2010 Code development process | 3 |
| 9./10.) Research for hurricane resistance Code enhancements window/water leakage window/wall interface soffit performance | 4 |
| 28.) CO detectors recommendations | 5 |
| 35.) Develop plan to implement legislated energy efficiency increases | 6 |
| 27.) Criteria for cost effectiveness test for increases in energy efficiency | 7 |
| 30.) Develop list of evaluation entities & report to Legislature, or develop criteria for approving evaluation entities by rule | 8 |
| 26./11.) Indoor Humidity & Moisture Control | 9 |
| 16.) Efficiency standards for energy using products | 10 |
| 38.) Evaluate adoption of flood standards in FBC (DEM, FEMA) | 11 |
| 25.) Bedroom definition for septic tank sizing with DOH | 12 |
| 33.) Entrapment standards for existing pools | 13 |
| 37.) Evaluate equivalency of ASTM E 1300-02 and 04 & self affirmation for PA Rule 9B-72 | 14 |
| 24.) Soffit system labeling requirements | 14 |
| 32.) Design charette for hotel room accessibility | 16 |
| 31.) Develop enhancements for gravel roof systems | 17 |
| 34.) Evaluate rainwater collection and use with DOH | 18 |
| 36.) Evaluate need for Code Core Course requirement for licensing | 19 |
| 29.) Criteria for energy efficient pool systems | 20 |

TASKS DIRECTED BY LAWS

2008 Legislature Directed Tasks

HB 697		Building Code

Action required:

1.  Recommend the Legislature expand the list of evaluation entities in law or develop and adopt rules for approving evaluation entities.

“Section 16. Subsection (17) is added to section 553.842,Florida Statutes, to read:

553.842 Product evaluation and approval.—

(17)(a) The Florida Building Commission shall review the list of evaluation entities in 	subsection (8) and, in the annual report required under s. 553.77, shall either recommend 	amendments to the list to add evaluation entities the commission determines should be 	authorized to perform 	product evaluations or shall report on the criteria adopted by rule or 	to be adopted by rule allowing the commission to approve evaluation entities that use the 	commission's product 	evaluation process. If the commission adopts criteria by rule, the 	rulemaking process must be completed by July 1, 2009.”

HB 7135	Energy

Action required:

- Increase building efficiency requirements of the 2010 Florida Energy Efficiency Code for Building Construction by 5% for the 2010 relative to the Code which takes effect December 31, 2009.

- Identify specific building options to achieve the energy efficiency improvements.

- Adopt by rule a cost effectiveness test and apply to the energy efficiency improvements.

“Section 109. Section 553.9061, Florida Statutes, is created to read:

553.9061 Scheduled increases in thermal efficiency standards.--

(1) The purpose of this section is to establish a schedule of increases in the energy 	performance of buildings subject to  the Florida Energy Efficiency Code for Building 	Construction. The Florida Building Commission shall:

(a) Include the necessary provisions by the 2010 edition of the Florida Energy		  Efficiency Code for Building Construction to increase the energy performance of new buildings by at least 20 percent as compared to the energy efficiency provisions of the 2007 Florida Building Code adopted October 31, 2007.

:

:

(2) The Florida Building Commission shall identify within code support and compliance 	documentation the specific building options and elements available to meet the energy 	performance goals established in subsection (1). Energy-efficiency performance options and 	elements include, but are not limited to:

(a) Solar water heating.

(b) Energy-efficient appliances.

(c) Energy-efficient windows, doors, and skylights.

(d) Low solar-absorption roofs, also known as "cool roofs."

(e) Enhanced ceiling and wall insulation.

(f) Reduced-leak duct systems.

(g) Programmable thermostats.

(h) Energy-efficient lighting systems.

(3) The Florida Building Commission shall, prior to implementing the goals established in 	subsection (1), adopt by rule and implement a cost-effectiveness test for proposed increases 	in energy efficiency. The cost-effectiveness test shall measure cost-effectiveness and shall 	ensure that energy efficiency increases result in a positive net financial impact.”

Section 110. Subsection (1) of section 553.909, Florida Statutes, is amended, subsections (3) and (4) are renumbered as subsections (6) and (7), respectively, and new subsections (3), (4), and (5) are added to that section, to read:

553.909 Setting requirements for appliances; exceptions.--

1) The Florida Energy Efficiency Code for Building Construction shall set the minimum requirements for commercial or residential swimming pool pumps, swimming pool water heaters, and heat traps and thermostat settings for water heaters used to heat potable water sold for residential use. The code shall further establish the minimum acceptable standby loss for

electric water heaters and the minimum recovery efficiency and standby loss for water heaters fueled by natural gas or liquefied petroleum gas.

(3) Commercial or residential swimming pool pumps or water heaters sold after July 1, 2011, shall comply with the requirements of this subsection. Natural gas pool heaters shall not be equipped with constantly burning pilots. Heat pump pool heaters shall have a coefficient of performance at low temperature of not less than 4.0. The thermal efficiency of gas fired pool heaters and oil-fired pool heaters shall not be less than 78 percent. All pool heaters shall have a readily accessible on-off switch that is mounted outside the heater and that allows shutting off the heater without adjusting the thermostat setting.

(4) Pool pump motors shall not be split-phase, shaded pole, or capacitor start-induction run types. Residential pool pumps and pool pumps motors with a total horsepower of 1 HP or

more shall have the capability of operating at two or more speeds with a low speed having a rotation rate that is no more than one-half of the motor's maximum rotation rate. Residential

pool pump motor controls shall have the capability of operating the pool pump at a minimum of two speeds. The default circulation speed shall be the residential filtration speed, with a higher speed override capability being for a temporary period not to exceed one normal cycle or 120 minutes, whichever is less. Except that circulation speed for solar pool heating systems shall be permitted to run at higher speeds during periods of usable solar heat gain.

(5) Portable electric spas standby power shall not be greater than 5(V2/3) watts where V = the total volume, in gallons, when spas are measured in accordance with the spa industry test protocol.

2007 Legislature Directed Tasks- Regular Session

CS/HB 7123	Energy

Action required:

- Form Work Group and Develop model energy efficiency ordinance for residential construction.

- Conduct study to evaluate cost effective baseline for Florida Energy Code residential requirements, determine cost effective standards for commercial buildings and compare to the International Energy Conservation Code and ASHRAE 90.1 and 90.2 in consultation with designated others.

- Develop and implement a public awareness campaign on energy efficiency and benefits of Green Building in consultation with others.

- Work with DCA to evaluate updated energy efficiency standards for energy using products

CS/HB 7057	Wind Loss Mitigation Studies and FBC Mitigation Requirements and Standards

Action required:

- Consult with Office of Insurance Regulation on “lost cost relativities” study.

- Develop mitigation techniques for retrofit of existing site-built residential buildings:

  - Prescriptive gable end bracing techniques

  - Secondary water barrier requirements and standards

  - Prescriptive roof-to-wall attachment techniques (not to exceed 	15% of reproofing cost)

  - Strengthening/correction roof deck attachment/fastening

  - Opening protection

3.	Adopt for site-built residential buildings by October 1, 2007:

- Mitigation techniques

- Requirement that roof replacement requires secondary water barrier and roof deck attachment/fastening

- Requirement that within WBD region roof replacement for buildings insured for $300K or more must also have roof-to-wall connections upgraded

- Requirement that any permitted activity valued at $50K or more for buildings located within the WBD region and insured for $750K or more must also provide for openings protection

4.	Adopt in 2007 FBC:

  - Requirements of 2) and 3).

CS for CS for SB 2836	Building Code

Action required:

- Electrical bonding and grounding for swimming pool decks:

  - Notify building departments about pool bonding alternative authorized by law.

  - Review swimming pool electrical bonding requirements of NEC and develop alternative technique.

  - Adopt a rule authorizing use of the alternative technique.

  - Adopt the alternative in the 2007 FBC.

- Gravel or stone roofing systems

a)  Determine and document the following if eliminate systems from Code:

- Scientific basis or reason for elimination

- An available alternative equivalent in cost and durability

- Whether elimination will unnecessarily restrict or eliminate business or consumer choice in roofing systems

- Whether elimination will negatively affect the nesting habitat of any species of nesting bird; coordination with Fish and Wildlife Conservation Commission

b)  Adopt a rule by chap 120 to preserve use of gravel or stone roofing systems if 	 		the above conditions cannot be determined and documented

- Warehouse expansion sprinkler requirements:

- Review modifications 2151, 2152, 2153, and 2492 and determine based on public comment if there is a continuing need for any Florida specific requirement of the Code the modifications seek to repeal

- Adopt or modify the modifications by chapter 120 only for inclusion in next edition of FBC

- Energy Code evaluation-

- Conduct study to evaluate cost effective baseline for Florida Energy Code residential requirements, determine cost effective standards for commercial buildings and compare to the International Energy Conservation Code and ASHRAE 90.1 and 90.2 in consultation with designated others.

CS for CS for SB 1822	Carbon Monoxide Detectors

Action required:

- Adopt a rule to require CO detectors in buildings with fossil fuel burning heater or appliance (including boiler in public lodging), fireplace, or attached garage and rooms used for sleeping purposes effective by July 1,2008.

- Include requirements in next revision/(edition) of FBC.

- Work with DBPR on chapter 4, FBC, Building requirements for public lodging buildings with both sleeping rooms and combustion fired boilers in the building.

CS for SB 404	Sprinkling Existing Portions of Warehouse Expansions

Action required:

- Post notice of statutory requirement on website and notify building departments.

- Include new provision of law in 2007 FBC update.

CS for SB 2498	Delayed Elimination of Design for Internal Pressure

Action Required:

- Notification to building departments and industry.

2007 Legislature Directed Tasks- Special Session

Florida Building Code Amendments:

- “…eliminate all exceptions that provide less stringent requirements.” than the 2006 IBC and IRC for wind-borne debris protection.

[HB 1A Section 10 (1)]

Citizens Insurance criteria for buildings built within 2500 feet of the coast after 2009:

- “…develop voluntary “Code Plus” guidelines for increasing the hurricane resistance of buildings.”

[HB 1A Sections 10 (2) and 21 627.351(6)(a)6.]

2006 Legislature Directed Tasks

Florida Building Code Amendments:

- Re-designate the Wind Borne Debris Protection Region for the Florida Panhandle

COMPLETED

2005 Legislature Directed Tasks

Florida Building Code Amendments:

Expedited Code Amendment

COMPLETED

- Shall by November 1, 2005, adopt the ICC provisions for ventless attic spaces. [Section 33 SB 442]

- Shall by November 1, 2005, recognize all alarms complying with UL 2017 for the pool alarm option compliance with swimming pool safety requirements of chapter 515 , F.S. [Section 32 SB 442]

- Shall consider how to address water intrusion and roof-covering-attachment weaknesses. [Section 34 SB 442]

- Shall review Modifications 569 and 570 adopted October 14, 2003 to IBC and repeal, modify or leave the same but 569 and 570 cannot go into effect until the review (leave the same) or rulemaking (modify or repeal) are completed. [Section 48 SB 442]

2004 FBC Glitch Amendments (2006 Annual Amendment to 2004 FBC)

COMPLETED (Implemented in the 2005 expedited Code Amendment)

- Shall amend the 2004 FBC to allow use of the area under mezzanines to be included in the calculation of total floor area when determining the maximum allowable mezzanine area in sprinklered S2 occupancies of Type III construction. Retroactive to the adoption of the 2001 FBC. [Section 44 SB 442]

- Shall modify Table 1014.1 of 2004 FBC maximum occupancy loads for R occupancies. [Section 46 SB 442]

- Shall amend section 1014.1.2 of 2004 FBC to exempt R1 and R2 occupancies from required distance between exits under certain conditions. [Section 46 SB 442]

2007 Florida Building Code Update

- Eliminate the “interior pressure design” option for buildings in the wind-borne debris regions consistent with the IBC and IRC.

Special Studies:

- Together with building officials from the area, review Hurricane Ivan damage and other data for the region from Franklin County to the Alabama border and issue a report of findings and recommendations to the Governor and 2006 Legislature. [Section 39 SB 442]

- Evaluate the definition of exposure category C and make recommendations to the Governor and 2006 Legislature. [Section 41 SB 442]

- Study the recommendation that the State be served by a single validation entity for state product approval. [Section 45 SB 442]

Other Tasks:

COMPLETED

- Develop a form by rule that is posted on a construction site and identifies all private providers that will be conducting inspections and their contact information. [Section 11 SB 442/ 553.791(4)(c)]

- Develop a form by rule for use on the Building Code Information System for petitioning for review of local building official decisions. [Section 9 SB 442/ s.553.775(3)(c)2.]

- Add design and construction related facility licensing requirements for Hospice Facilities. [HB 189]