**Hold Glitch Correction Phase after the Effective Date of the 6th Edition (2017) FBC, if needed - Rulemaking via Integrated Code – Adopted Unanimously by the Commission August 18, 2015**

**6thEdition (2017) FBC Code Update Development Tasks**

|  |
| --- |
| **12. 6th Edition (2017) Update to the Florida Building Code**  |
| **Task** | **Schedule** |
| ***Primary Code Development Phase:*** |  |
|  2014 NEC published and available to the public; | 08/2013 |
|  2015 International Codes published and available to the public; | 05/2014 |
|  Commission selects 2015 I Codes and 2014 NEC as foundation for 6th Edition (2017) FBC *(****April 2015 Commission meeting)*** | 04/14/2015 |
|  Staff evaluates Florida amendments resulting from direction of the Legislature and Commission initiatives to propose for inclusion in the 6th Edition (2017) FBC and publish “**Preliminary Supplement**”. Amendments are compiled in 2015 I – Codes format. | 3/2015 – 6/2015 |
| 2015 I Codes plus the Preliminary Supplement – posted online | 6/30/2015 |
|  Period for public to propose modifications to the 2015 I Codes and the **Preliminary Supplement** | 7/1/2015 – 1/3/2016 |
| Proposed amendments reviewed by staff and posted to the Commission website | 1/13/2016 |
| 1st 45 day comment period ends ***(By law -45 day min before TAC review)*** | 2/25/2016 |
| Staff post on Commission website proposed code changes (Tracking Charts and Detail Reports)  | 3/21/2016 |
| TACs consider proposed modifications including comments from the 1st 45 day comment period and adopt recommendationsTACs meetings - 4-day on-site meetings in conjunction with the April 2016 Commission meeting | 4/1-15/2016 |
| TACs recommendations posted to the website | **5/6/**2016 |
| 2nd 45 day comment period ends ***(by law – 45 day min before Commission review)*** | 6/21/2016 |
| Staff post on Commission website proposed code changes with comments (Tracking Chats and Details Reports) | 6/30/2016 |
| TACs consider public comments on their actions and prepare public comment for consideration by the Commission.TACs meetings – 4-day meetings [2-day on-site (Gainesville) and 2 – day via conference/webinar]  | 7/18-21/2016 |
| Staff post on Commission website TACs consideration of public comments | 8/1/2016 |
| Commission considers TAC recommendations at **~~Rule development Workshops~~** - Commission – 2-day meeting | 8/16-17/2016 |
| Draft 6th Edition (2017) FBC (Florida Supplement plus I Codes) posted online**Provide Supplements to ICC for integration into the 2015 I-Code** | 9/19/2016 |
| **Rule development Workshops** | **12/13/2016** |
| Integrated Draft 6th Edition (2017) FBC – Posted online | 4/21/2017 |
| ***Final Rule Hearing*** on 6th Edition (2017) FBC/Commission approves final version of Code6th Edition (2017) Florida Fire Prevention Code available in final format | **6/8/2017** |
|  Rule Submitted to Secretary of State and Supplement/Integrated posted online – subject to addressing all JAPC’s concerns | **TBD** |
|  Printed Code available - subject to negotiation with ICC | **TBD** |
|  2017FBC **(6th edition)** effective date (6 – months after publication) | **12/31/2017** |
| ***Glitch Correction Phase: after effective date, if needed*** |  |
|  Period to propose glitch modifications to draft 6th Edition (2017) FBC | **TBD** |
|  Post Tracking/Detail reports online | **TBD** |
|  TACs consider proposed glitch modifications and develop public  comment via conference call/Webinars | **TBD** |
|  Commission considers proposed glitch mods and TAC comments (Rule Development Workshop)Commission – 2-day meeting | **TBD** |
|  Draft Supplement to the 6th Edition (2017) FBC posted online  | **TBD** |
|  ***Final Rule Hearing*** on adoption of the Supplement to the 6th Edition (2017) FBC/Commission | **TBD** |
|  Rule Submitted to Secretary of State and Supplement posted online – subject to addressing all JAPC’s concerns | **TBD** |
|  Final supplement available for download | **TBD** |
|  Supplement to 2017 FBC **(6th edition)** effective date  | **TBD** |
|  |  |
| 553.73(7)(e) A rule updating the Florida Building Code in accordance with this subsection shall take effect no sooner than 6 months after publication of the updated code. Any amendment to the Florida Building Code which is adopted upon a finding by the commission that the amendment is necessary to protect the public from immediate threat of harm takes effect immediately. |