**8thEdition (2023) FBC Code Update Development Tasks**

|  |  |
| --- | --- |
| **8th Edition (2023) Update to the Florida Building Code—** | |
| **Tasks** | **Schedule** |
| ***Selection of the model codes:*** |  |
| 2020 NEC published and available to the public; | 08/25/2019 |
| 2021 International Codes published and available to the public; | January 2021 |
| Commission selects 2021 I Codes “model codes” and 2020 NEC to conduct its review | 2/9/2021  Completed |
| ***Review of the model code changes:*** |  |
| In coordination with ICC, staff post complete listing of the code changes to the I Codes online | 2/25/2021  Completed |
| Staff post on Commission website/Building Code Information System (BCIS) analysis of the 2021 I-Code change to provide for identification of the following:  - Provisions which overlap with the provisions of the FBC  - Provisions which correlate directly with the provisions of the FBC  - Provisions which provide for energy efficiency standards that meet or  exceed the national energy standards mandated by Title III of the Energy  Conservation and Protection Act  - Provisions which are necessary to maintain eligibility for federal funding  and discounts from the National Flood Insurance Program, the Federal  Emergency management Agency, or the United States Department of  Housing and Urban Development | 5/17/2021  Completed |
| Residential Construction Cost Impact Workgroup (RCCIWG) reviews the 2021 changes to the International Residential Code (IRC) and provides comments to the Commission’s TACs on impactful code changes.  RCCIWG meeting – Conference call/Webinar | 6/29/2021  Completed |
| 45 day public review and comment period ends ***(By Rule -45 day min before TAC review)*** | 7/1/2021  Completed |
| Staff post on Commission website analysis of the 2021 I-Code changes with public comments  (Tracking Charts and code change monographs) | 8/2/2021  Completed |
| TACs review the 2021 changes to the I Codes and make recommendations to the Commission regarding those changes as follows:  That the Commission rejects certain model code provisions by consent agenda.    (Due to such issues as being unnecessary, negatively impacting the level of public  health, safety, or general welfare provided by an existing Florida Building Code  provision, diminishing the requirements of provisions related to wind resistance or  water intrusion, unnecessarily imposing additional costs, or potentially requiring  modification or further investigation before being adopted for use in this state)  That the Commission approves certain model code provisions by consent agenda.  (When considering whether to recommend inclusion on a consent agenda for  approval, the TACs shall consider such criteria as whether the model code  provisions are editorial or organizational in nature, correct an error, provide  clarification, provide for alternative design methods, improve the effectiveness of  the code, are uncontroversial to affected stakeholders, or are required by law.)  That the Commission approve or reject certain model code provisions after considering them individually  (When recommending individual consideration of model code updates, the TACs  shall consider such criteria as whether the update has the potential to impose  significant costs, cause confusion or regulatory difficulty, may be unnecessary, is  highly controversial to affected stakeholders, or requires further evaluation.)  TACs meetings – on site - TBD | 9/22-30/2021 and 10/1-7/2021  Completed |
| Staff post TACs’ recommendations online for further public review | 10/15/2021  Completed |
| Deadline for requesting amendments (2021 I-Codes changes) to be pulled of the consent agenda for individual consideration | **11/19/2021**  Completed |
| Commission considers TACs’ recommendations regarding the latest changes to the model codes - on site meeting (TBD) | 12/14-15/2021  Completed |
| Staff post Commission’s recommendations online | 1/3/2022  Completed |
| ***Proposed modification to the foundation code and Commission’s approved I –Codes changes*** |  |
| Period for public to propose modifications to the 7th Edition (2020) FBC and the Commission’s approved I-Codes changes | **1/4/2022 – 2/15/2022**  Completed |
| Proposed amendments reviewed by staff and posted to the Commission website | 3/3/2022  Completed |
| 1st 45 day comment period ends ***(By law -45 day min before TAC review)*** | **4/17/2022** |
| Staff post on Commission website proposed code changes (Tracking Charts and Detail Reports)  **Staff assign TAC members specific proposed code change for review in advance of the TAC meetings in June** | 5/2/2022  Completed |
| TACs consider proposed modifications (1st 45 day comment period)  TACs meetings - 4-day on-site meetings | **6/20-24/2022**  Completed |
| TACs recommendations posted to the website Starting date for the 2nd 45 day comment period | 7/1~~2~~ 3/2022 |
| Residential Construction Cost Impact Workgroup (RCCIWG) reviews the TACs’ recommendations with regard to the proposed modifications to the Florida Residential Code (FRC) and provides comments to the TACs/Commission on impactful code changes.  RCCIWG meeting – Conference call/webinar | 8/17/2022 |
| 2nd 45 day comment period ends ***(by law – 45 day min before Commission review)*** | **8/26/2022** |
| Staff post on Commission website proposed code changes with comments (Tracking Chats and Details Reports) | 9/21/2022 |
| TACs consider public comments on their actions on the proposed mods  TACs meetings – 4-day meetings [2-day on-site (TBD) and 2 – day via conference/webinar] – As needed and as applicable | **10/5-13/2022** |
| Staff post on Commission website TACs consideration of public comments | 11/10/2022 |
| Deadline for requesting amendments to be pulled of the consent agenda for individual consideration | 11/22/2022 |
| Commission considers TAC recommendations (2nd 45 day comment period)  Commission – 2-day meeting | **12/13-14/2022** |
| 8th Edition (2023) FBC (7th Edition (2020) FBC, Florida Supplement and Commission’s approved I Codes) posted online | ~~1/19/2023~~  12/20/2022 |
| ***Provide Supplements to ICC for integration into the 7th Edition (2020) FBC*** |  |
| Deadline for submitting comments on the draft 8th Edition (2023) update to the FBC (Supplements plus 7th Edition (2020) FBC) | January 31, 2023 |
| TACs review comments to Rule Development Workshop of March 14, 2023 and make recommendations to the Commission  TACs meetings - 6-day conference call/webinar meetings | 2/15-24/2023 |
| **Rule development Workshop**  Commission – 1-day meeting | March 14, 2023 |
| Integrated Draft 8th Edition (2023) FBC – Posted online | **May 22, 2023** |
| ***Hearing*** on 8th Edition (2023) FBC to consider received comments | TBD |
| ***Final Rule Hearing*** on 8th Edition (2023) FBC/Commission approves final version of Code  8th Edition (2023) Florida Fire Prevention Code available in final format | TBD |
| Rule Submitted to Secretary of State and Supplement/Integrated posted online – subject to addressing all JAPC’s concerns | TBD |
| Final FBC -PDF posted | TBD |
| Printed Code available - subject to negotiation with ICC | TBD |
| 2023 FBC **(8th edition)** effective date (6 – months after publication) | **12/31/2023** |
|  |  |
| 553.73(7)(e) A rule updating the Florida Building Code in accordance with this subsection shall take effect no sooner than 6 months after publication of the updated code. Any amendment to the Florida Building Code which is adopted upon a finding by the commission that the amendment is necessary to protect the public from immediate threat of harm takes effect immediately. | |