## Dry Glazed
ID | Manufacturer | Category | Subcategory | Compliance Method | Type of Missile (1) | Gaskets Testing Indicated | Spacer Identified | Email Sent | Notes
FL12126 | Vistawall Architectural Products 803 Airport Road Terrell, TX 75160 | Panel Walls | Curtain Walls | Evaluation by PE | Large | No | No | 2011-08-15 | Recommended for Revocation kwest@oldcastleglass.com bounced forwarded to kblays@oldcastlebe.com (8/16/11) No response as of 09/28/11 Registered Letter Sent 10/03/11 Registered Letter Received 10/08/11 Email send requesting the applicant to withdraw 11/07/11 with no response
FL13055-R0 | YKK AP America 332 Firetower Road Dublin, GA 31021 | Panel Walls | Storefronts | Evaluation by PE | Large .2 Large .6 | Yes | No | 2011-08-15 | Recommended for Revocation email bounced forwarded to Chris Moody No response as of 09/28/11 Registered Letter Sent 10/03/11 Registered Letter Received 10/06/11 Sent an email to David Oliver and Scott Blake on 11/1/11 Response from David Oliver 11/1/11: The other two approvals in question, FL 12543 and FL 13055, are being addressed currently. We are waiting on Al Farooq Corporation engineering documentation to be complete. Then we will add the new engineering documentation to our existing FL 14218 so we can consolidate our YHS 50 into one approval. When this is complete I will ask for these two approvals in question to be withdrawn as well. These may be done for the January meeting. Chris Moody has more information on this matter if more clarification is needed.
FL12543 | YKK AP America 332 Firetower Road Dublin, GA 31021 | Panel Walls | Curtain Walls | Certification (NOA) | Small .2 | No | No | 2011-08-15 | Recommended for Revocation No response as of 09/28/11 Registered Letter Sent 10/03/11 Registered Letter Received 10/06/11 Sent an email to David Oliver and Scott Blake on 11/1/11 Response from David Oliver 11/1/11: The other two approvals in question, FL 12543 and FL 13055, are being addressed currently. We are waiting on Al Farooq Corporation engineering documentation to be complete. Then we will add the new engineering documentation to our existing FL 14218 so we can consolidate our YHS 50 into one approval. When this is complete I will ask for these two approvals in question to be withdrawn as well. These may be done for the January meeting. Chris Moody has more information on this matter if more clarification is needed.
FL11634 | EFCO Corporation 1000 County Road Monett, MO 65708 | Panel Walls | Storefronts | Evaluation by PE | Large .2 | No | No | 2011-08-15 | In Process of Compliance FL11634-R1 Applied for 11/07/2011 No response as of 09/28/11 Registered Letter Sent 10/03/11 Registered Letter Received 10/7/11 Left a voicemail and sent an email on 11/01/11
FL8787-R2 | Kawneer Company, Inc. | Panel Walls | Storefronts | Certification (NOA) | Large .2 Small .3 | Yes Yes | No No | 2011-08-15 | In Process of Compliance The applicant was granted 60 days until the completion date of the December 2011 meeting.
FL5388-R3 | Kawneer Company, Inc. | Panel Walls | Curtain Walls | Certification (NOA) | Small .4 Small .6 | No | No | 2011-08-15 | In Process of Compliance The applicant was granted 60 days until the completion date of the December 2011 meeting.
FL7359-R2 | Kawneer Company, Inc. | Panel Walls | Storefronts | Certification (NOA) | Small .2 | No | No |  | In Compliance FL7359-R3 Is Pending FBC Approval
FL13340 | Kawneer Company, Inc. | Windows | Fixed | Evaluation by PE | Large | Yes | No | 2011-08-15 | In Compliance FL13340-R1 Pending FBC Approval 10/16/2011
FL12359 | Sun Metals Systems, Inc. | Windows | Fixed | Evaluation by PE | Large | Yes | Yes |  | In Compliance
FL12007-R0 | Vistawall Architectural Products 803 Airport Road Terrell, TX 75160 | Panel Walls | Storefronts | Evaluation by PE | Large .2 | No | No | 2011-08-15 | In Compliance kwest@oldcastleglass.com bounced forwarded to kblays@oldcastlebe.com (8/16/11) No response as of 09/28/11 Registered Letter Sent 10/03/11 Registered Letter Received 10/08/11 Spoke with Kathy Blays, and she has sent a request to Withdraw this application on 11/1/11
FL12809-R2 | West Tampa Glass Company | Panel Walls | Curtain Walls | Evaluation by PE | Large | Yes | Yes |  | In Compliance
FL12453 | YKK AP America 332 Firetower Road Dublin, GA 31021 | Panel Walls | Storefronts | Evaluation by PE | Large .2 Large .6 | Yes | No | 2011-08-15 | In Compliance email bounced forwarded to Chris Moody No response as of 09/28/11 Registered Letter Sent 10/03/11 Registered Letter Received 10/06/11 Sent an email to David Oliver and Scott Blake on 11/1/11 Davlid Oliver has asked to withdraw the application 11/1/11
FL14218-R1 | YKK AP America | Panel Walls | Storefronts | Evaluation by PE | Small .1 Small .4 | Yes | Yes |  | In Compliance
FL12456 | YKK AP America | Panel Walls | Curtain Walls | Certification (NOA) | Small .3 | No | No |  | In Compliance FL12456-R1 Approved 10/11/2011
FL13252-R1 | YKK AP America | Panel Walls | Curtain Walls | Evaluation by PE | Small .3 Large .4 | Yes | Yes |  | In Compliance
(1) Decimal figure represents the sequnce of the product on the application
Note: This is a report of insulated dry glazed products in order to verify that spacer was identified. Insulated dry glazed systems
are difficult to identify within the datbase and ommissions are likely.
Resolved

## ALL HVHZ Storefronts
Search Criteria |  | Refine Search
Code Version | 2007 | FL# | ALL
Application Type | ALL | Product Manufacturer | ALL
Category | Panel Walls | Subcategory | Storefronts
Application Status | Approved | Compliance Method | ALL
Quality Assurance Entity | ALL | Quality Assurance Entity Contract Expired | ALL
Product Model, Number or Name | ALL | Product Description | ALL
Approved for use in HVHZ | Yes | Approved for use outside HVHZ | Yes
Impact Resistant | Yes | Design Pressure | ALL
Other | ALL
FL1610-R3 | Revision | Vistawall Architectural Products | Joshua M Royce, PE | Approved | NOA
History |  | Category: Panel Walls | (717) 676-5202 |  | dry glazed
Subcategory: Storefronts
FL1899-R4 | Revision | Alumiglass, Inc. | Jorge A. Pomerantz, P.E. | Approved | Evaluation
History |  | Category: Panel Walls | (954) 394-8521
Subcategory: Storefronts
FL2887-R3 | Revision | Vistawall Architectural Products | Joshua M Royce, PE | Approved | NOA
History |  | Category: Panel Walls | (717) 676-5202
Subcategory: Storefronts
FL5145-R1 | Revision | Hurricane Manufacturing Corp | Jesus Gonzalez, P.E. | Approved *
History |  | Category: Panel Walls | (704) 827-1769 |  | NOA
Subcategory: Storefronts
FL5499-R1 | Revision | Elite Aluminum Corporation | Jorge A. Pomerantz, P.E. | Approved
History |  | Category: Panel Walls | (954) 394-8521 |  | Evaluation
Subcategory: Storefronts
FL6159-R1 | Revision | Nova Comm Inc. | Steven M. Urich, PE | Approved
History |  | Category: Panel Walls | (717) 932-8500 |  | NAMI
Subcategory: Storefronts
FL6297-R3 | Revision | Arch Aluminum and Glass Co., Inc. | Miami-Dade BCCO - VAL | Approved
History |  | Category: Panel Walls | (786) 315-2590 |  | NOA
Subcategory: Storefronts
FL6622-R1 | Affirmation | Atlas Window Systems Inc. |  | Approved
History |  | Category: Panel Walls |  |  | expired NOA
Subcategory: Storefronts
FL7359-R2 | Revision | Kawneer Company, Inc. | Miami-Dade BCCO - VAL | Approved
History |  | Category: Panel Walls | (786) 315-2590 |  | NOA
|  | Subcategory: Storefronts |  |  | dry glazed
FL8731-R1 | Affirmation | YKK AP America | Joseph A Reed, PE | Approved
History |  | Category: Panel Walls | (717) 764-7700 |  | Evaluation
|  | Subcategory: Storefronts |  |  | dry glazed/tested
FL8787-R2 | Revision | Kawneer Company, Inc. | Miami-Dade BCCO - VAL | Approved
History |  | Category: Panel Walls | (786) 315-2590 |  | NOA
|  | Subcategory: Storefronts |  |  | dry glazed
FL9449-R2 | Revision | United States Aluminum Corp. | Joshua M Royce, PE | Approved
History |  | Category: Panel Walls | (717) 676-5202 |  | NOA
Subcategory: Storefronts
FL9556-R1 | Affirmation | Atlas Window Systems Inc. |  | Approved
History |  | Category: Panel Walls |  |  | Nami
Subcategory: Storefronts
FL10416-R1 | Affirmation | Coral Industries, Inc | Charles H. Moss, P.E. | Approved
History |  | Category: Panel Walls | (770) 786-3163 |  | Test Report
Subcategory: Storefronts
FL10467-R1 | Affirmation | Coral Industries, Inc | Charles H. Moss, P.E. | Approved
History |  | Category: Panel Walls | (770) 786-3163 |  | Evaluation
Subcategory: Storefronts
FL10606 | New | Custom Glass Company | Miami-Dade BCCO - VAL | Approved | expired NOA
|  | Category: Panel Walls | (786) 315-2590
Subcategory: Storefronts
FL10609 | New | Custom Glass Company | Miami-Dade BCCO - VAL | Approved | expired NOA
|  | Category: Panel Walls | (786) 315-2590
Subcategory: Storefronts
FL10845 | New | Kawneer Company, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Panel Walls | (786) 315-2590
Subcategory: Storefronts
FL11627 | New | Elite Aluminum Corporation | James L. Buckner, P.E. at CBUCK Engineering | Approved | Evaluation
|  | Category: Panel Walls | (561) 491-9927
Subcategory: Storefronts
FL11634 | New | EFCO Corporation | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Panel Walls | (717) 676-5202 |  | Dry glazed
Subcategory: Storefronts
FL11978 | New | Kawneer Company, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Panel Walls | (786) 315-2590
Subcategory: Storefronts
FL12007 | New | Vistawall Architectural Products | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Panel Walls | (717) 676-5202 |  | dry glazed
Subcategory: Storefronts
FL12030 | New | EFCO Corporation | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Panel Walls | (717) 676-5202
Subcategory: Storefronts
FL12131 | New | Vistawall Architectural Products | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Panel Walls | (717) 676-5202
Subcategory: Storefronts
FL12239 | New | Elite Aluminum Corporation | James L. Buckner, P.E. at CBUCK Engineering | Approved | Evaluation
|  | Category: Panel Walls | (561) 491-9927
Subcategory: Storefronts
FL12543 | New | YKK AP America | Manhar K Jadav, P.E. | Approved | Evaluation
|  | Category: Panel Walls | (352) 589-1883 |  | dry glazed
Subcategory: Storefronts
FL13055 | New | YKK AP America | Manhar K Jadav, P.E. | Approved | Evaluation
|  | Category: Panel Walls | (352) 589-1883 |  | dry glazed
Subcategory: Storefronts
FL13523 | New | United States Aluminum Corp. | Joshua M Royce, PE | Approved | NOA
|  | Category: Panel Walls | (717) 676-5202
Subcategory: Storefronts
FL13927 | New | E.S. Windows, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Panel Walls | (786) 315-2590
Subcategory: Storefronts
FL14218-R1 | Revision | YKK AP America | Shawn G. Collins, PE | Approved | Evaluation
History |  | Category: Panel Walls | (813) 992-5195 |  | dry glazed
Subcategory: Storefronts
FL14219 | New | Hurricane Manufacturing Corp | Jesus Gonzalez, P.E. | Approved * | NOA
|  | Category: Panel Walls | (704) 827-1769
Subcategory: Storefronts
FL14220 | New | Hurricane Manufacturing Corp | Jesus Gonzalez, P.E. | Approved * | NOA
|  | Category: Panel Walls | (704) 827-1769
Subcategory: Storefronts
FL14289 | New | Crawford Tracey Corporation | Jesus Gonzalez, P.E. | Approved | Evaluation
|  | Category: Panel Walls | (704) 827-1769
Subcategory: Storefronts
FL14325 | New | OLDCASTLE BUILDING ENVELOPE | Rene J.Quiroga, PE | Approved | Evaluation
|  | Category: Panel Walls | (407) 681-6595
Subcategory: Storefronts

## ALL HVHZ Curtain Walls
Search Criteria |  | Refine Search
Code Version | 2007 | FL# | ALL
Application Type | ALL | Product Manufacturer | ALL
Category | Panel Walls | Subcategory | Curtain Walls
Application Status | Approved | Compliance Method | ALL
Quality Assurance Entity | ALL | Quality Assurance Entity Contract Expired | ALL
Product Model, Number or Name | ALL | Product Description | ALL
Approved for use in HVHZ | Yes | Approved for use outside HVHZ | Yes
Impact Resistant | Yes | Design Pressure | ALL
Other | ALL
FL2981-R2 | Revision | Wellbilt International | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Panel Walls | (786) 315-2590
Subcategory: Curtain Walls
FL3315-R1 | Revision | Harmon, Inc. | Joshua M Royce, PE | Approved | NOA
History |  | Category: Panel Walls | (717) 676-5202
Subcategory: Curtain Walls
FL5388-R3 | Revision | Kawneer Company, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Panel Walls | (786) 315-2590 |  | dry glazed
Subcategory: Curtain Walls
FL6286-R1 | Affirmation | YKK AP America | Architectural Testing, Inc | Approved | test report
History |  | Category: Panel Walls | (717) 764-7700
Subcategory: Curtain Walls
FL8162-R2 | Affirmation | EFCO Corporation |  | Approved | NOA
History |  | Category: Panel Walls |  |  | dry glazed
Subcategory: Curtain Walls
FL9921-R1 | Revision | Alumiglass, Inc. | Jorge A. Pomerantz, P.E. | Approved | Evaluation
History |  | Category: Panel Walls | (954) 394-8521
Subcategory: Curtain Walls
FL11488 | New | Kawneer Company, Inc. | James L. Buckner, P.E. at CBUCK Engineering | Approved | Evaluation
|  | Category: Panel Walls | (561) 491-9927
Subcategory: Curtain Walls
FL12001 | New | Vistawall Architectural Products | Robert A. Walz, PE | Approved | NOA
|  | Category: Panel Walls | (888) 262-9259
Subcategory: Curtain Walls
FL12081 | New | EFCO Corporation | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Panel Walls | (717) 676-5202
Subcategory: Curtain Walls
FL12126 | New | Vistawall Architectural Products | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Panel Walls | (717) 676-5202 |  | dry glazed
Subcategory: Curtain Walls
FL12133 | New | Vistawall Architectural Products | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Panel Walls | (717) 676-5202
Subcategory: Curtain Walls
FL12453 | New | YKK AP America | Robert A. Walz, PE | Approved | NOA
|  | Category: Panel Walls | (888) 262-9259 |  | dry glazed
Subcategory: Curtain Walls
FL12456 | New | YKK AP America | Robert A. Walz, PE | Approved | NOA
|  | Category: Panel Walls | (888) 262-9259 |  | dry glazed
Subcategory: Curtain Walls
FL12480-R1 | Revision | Sun Metals Systems, Inc. | Ryan J. King, P.E. | Approved | Evaluation
History |  | Category: Panel Walls | (813) 787-8283
Subcategory: Curtain Walls
FL12809-R2 | Revision | West Tampa Glass Company | Ryan J. King, P.E. | Approved | Evaluation
History |  | Category: Panel Walls | (813) 787-8283 |  | dry glazed
Subcategory: Curtain Walls
FL12943 | New | Enclos Corporation | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Panel Walls | (786) 315-2590
Subcategory: Curtain Walls
FL12945 | New | Enclos Corporation | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Panel Walls | (786) 315-2590
Subcategory: Curtain Walls
FL13250 | New | YKK AP America | Manhar K Jadav, P.E. | Approved | Evaluation
|  | Category: Panel Walls | (352) 589-1883 |  | dry glazed
Subcategory: Curtain Walls
FL13252-R1 | Revision | YKK AP America | Shawn G. Collins, PE | Approved | Evaluation
History |  | Category: Panel Walls | (813) 992-5195 |  | dry glazed
Subcategory: Curtain Walls
FL13255-R1 | Revision | YKK AP America | Manhar K Jadav, P.E. | Approved | Evaluation
History |  | Category: Panel Walls | (352) 589-1883 |  | dry glazed
Subcategory: Curtain Walls
FL13256-R1 | Revision | YKK AP America | Manhar K Jadav, P.E. | Approved | Evaluation
History |  | Category: Panel Walls | (352) 589-1883 |  | dry glazed
Subcategory: Curtain Walls
FL13433-R1 | Revision | YKK AP America | Manhar K Jadav, P.E. | Approved | Evaluation
History |  | Category: Panel Walls | (352) 589-1883 |  | dry glazed
Subcategory: Curtain Walls
FL14084 | New | Alumiglass, Inc. | Jorge A. Pomerantz, P.E. | Approved | Evaluation
|  | Category: Panel Walls | (954) 394-8521
Subcategory: Curtain Walls
FL14217-R1 | Revision | YKK AP America | Shawn G. Collins, PE | Approved | Evaluation
History |  | Category: Panel Walls | (813) 992-5195 |  | dry glazed
Subcategory: Curtain Walls
FL14313 | New | Crawford Tracey Corporation | Jesus Gonzalez, P.E. | Approved | Evaluation
|  | Category: Panel Walls | (704) 827-1769
Subcategory: Curtain Walls
FL14411-R1 | Revision | Crawford Tracey Corporation | Jesus Gonzalez, P.E. | Approved | Evaluation
History |  | Category: Panel Walls | (704) 827-1769
Subcategory: Curtain Walls

## Revised Fixed Windows
Search Criteria |  | Refine Search
Code Version | 2007 | FL# | ALL
Application Type | ALL | Product Manufacturer | ALL
Category | Windows | Subcategory | Fixed
Application Status | Approved | Compliance Method | ALL
Quality Assurance Entity | ALL | Quality Assurance Entity Contract Expired | ALL
Product Model, Number or Name | ALL | Product Description | ALL
Approved for use in HVHZ | Yes | Approved for use outside HVHZ | Yes
Impact Resistant | Yes | Design Pressure | ALL
Other | ALL
FL243-R9 | Revision | PGT Industries | Miami-Dade BCCO - VAL | Approved * | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL995-R3 | Revision | Kinro, Inc | Ryan J. King, P.E. | Approved | Evaluation
History |  | Category: Windows | (813) 787-8283
Subcategory: Fixed
FL1363-R4 | Affirmation | Pittsburgh Corning Corporation |  | Approved | NOA
History |  | Category: Windows
Subcategory: Fixed
FL1520-R3 | Revision | EFCO Corporation | Joshua M Royce, PE | Approved | NOA
History |  | Category: Windows | (717) 676-5202
Subcategory: Fixed
FL1648-R2 | Revision | Kolbe Windows and Doors - Wausau | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL2691-R2 | Revision | Windoworld Industries Inc. | National Accreditation & Management Institute, | Approved | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL3400-R1 | Revision | E.F. Bavis and Associates, Inc. | Locke Bowden | Approved | Evaluation
History |  | Category: Windows | (334) 300-1800
Subcategory: Fixed
FL4538-R1 | Revision | E.F. Bavis and Associates, Inc. | Locke Bowden | Approved | Evaluation
History |  | Category: Windows | (334) 300-1800
Subcategory: Fixed
FL5357-R2 | Affirmation | Pittsburgh Corning Corporation |  | Approved | Expired NOA
History |  | Category: Windows
Subcategory: Fixed
FL5358-R4 | Revision | PHILIPS PRODUCTS INC. | Ryan J. King, P.E. | Approved | AAMA
History |  | Category: Windows | (813) 787-8283 |  | NO QA Recommended for revocation
Subcategory: Fixed
FL5859-R3 | Revision | Custom Window Systems Inc. | Steven M. Urich, PE | Approved | Evaluation
History |  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL5919-R2 | Revision | Bell-View, Inc. | Joel Grenstein, P.E. | Approved | Evaluation
History |  | Category: Windows | (407) 629-8424
Subcategory: Fixed
FL6587-R1 | Revision | E.F. Bavis and Associates, Inc. | Locke Bowden | Approved | Evaluation
History |  | Category: Windows | (334) 300-1800
Subcategory: Fixed
FL7078-R1 | Revision | RC Aluminum Industries, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL7151-R2 | Revision | Marvin Windows and Doors | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL7156-R3 | Revision | Andersen Corporation | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL7361-R1 | Affirmation | MQ Window and Door |  | Approved | Expired NOA
History |  | Category: Windows
Subcategory: Fixed
FL7569-R1 | Affirmation | YKK AP America | Joseph A Reed, PE | Approved | Evaluation
History |  | Category: Windows | (717) 764-7700
Subcategory: Fixed
FL7822-R1 | Revision | Sun Metals Systems, Inc. | L.F. Schmidt, P.E. | Approved | Evaluation
History |  | Category: Windows | (813) 926-6537
Subcategory: Fixed
FL7829-R1 | Affirmation | YKK AP America Residential | Architectural Testing, Inc | Approved | Test report
History |  | Category: Windows | (717) 764-7700
Subcategory: Fixed
FL7882-R2 | Revision | Vi Win Tech | National Accreditation & Management Institute, | Approved | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL8166-R1 | Affirmation | EFCO Corporation |  | Approved | NOA
History |  | Category: Windows
Subcategory: Fixed
FL8784-R1 | Revision | Vi Win Tech | National Accreditation & Management Institute, | Approved | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL9063-R2 | Revision | CGI - Construction Glass Industries | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL9186-R1 | Revision | CGI - Construction Glass Industries | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL9217-R1 | Revision | Paradigm Window Solutions | Steven M. Urich, PE | Approved | AAMA
History |  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL9232-R1 | Revision | Paradigm Window Solutions | Steven M. Urich, PE | Approved | AAMA
History |  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL9292-R1 | Revision | Flesher Windows, Inc. | National Accreditation & Management Institute, | Approved | NAMI
History |  | Category: Windows | (804) 684-5124 |  | Expired
Subcategory: Fixed
FL9309-R1 | Affirmation | EFCO Corporation |  | Approved | NOA
History |  | Category: Windows
Subcategory: Fixed
FL9529-R1 | Revision | Entreprises Doco | National Accreditation & Management Institute, | Approved | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL9531-R1 | Revision | Entreprises Doco | National Accreditation & Management Institute, | Approved | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL9532-R1 | Revision | Entreprises Doco | National Accreditation & Management Institute, | Approved | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL9646-R1 | Revision | IVIV Group USA Corp | Steven M. Urich, PE | Approved | Evaluation
History |  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL9669-R1 | Revision | Eagle Window and Door, Inc | L.F. Schmidt, P.E. | Approved | Evaluation
History |  | Category: Windows | (813) 926-6537
Subcategory: Fixed
FL9674-R1 | Revision | Shwinco of Alabama, LLC. | National Accreditation & Management Institute, | Approved | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL9843-R1 | Revision | Hope's Windows, Inc. | Ryan J. King, P.E. | Approved | Evaluation
History |  | Category: Windows | (813) 787-8283
Subcategory: Fixed
FL9927-R2 | Revision | Silverline Building Products Corp. | Ryan J. King, P.E. | Approved | Evaluation
History |  | Category: Windows | (813) 787-8283
Subcategory: Fixed
FL9950-R1 | Revision | Reilly WoodWorks | Steven M. Urich, PE | Approved | Evaluation
History |  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL9956-R1 | Revision | Kolbe Windows and Doors - Manawa | Window and Door Manufacturers Association | Approved | WDMA
History |  | Category: Windows | (312) 673-4828
Subcategory: Fixed
FL10022-R1 | Revision | Pella Corporation | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL10084-R1 | Revision | Graham Architectural Products | Joel Grenstein, P.E. | Approved | Evaluation
History |  | Category: Windows | (407) 629-8424
Subcategory: Fixed
FL10376-R2 | Revision | The Hurricane Window and Door Factory | Steven M. Urich, PE | Approved | Evaluation
History |  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL11028-R1 | Revision | Window Craftsmen Inc. | National Accreditation & Management Institute, | Approved * | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL11057-R1 | Revision | EFCO Corporation | Steven M. Urich, PE | Approved | Evaluation
History |  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL11117-R3 | Revision | JELD-WEN | Miami-Dade BCCO - VAL | Approved * | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11448-R1 | Revision | Stanek Vinyl Windows | Locke Bowden | Approved | Evaluation
History |  | Category: Windows | (334) 300-1800 |  | FL11448-R2 is re-apply
|  | Subcategory: Fixed |  |  | .2 looks like its dry glazed?
FL11869-R3 | Revision | JELD-WEN | Miami-Dade BCCO - VAL | Approved *
History |  | Category: Windows | (786) 315-2590 |  | NOA
Subcategory: Fixed
FL12538-R1 | Revision | Sun Metals Systems, Inc. | Ryan J. King, P.E. | Approved
History |  | Category: Windows | (813) 787-8283 |  | Evaluation
Subcategory: Fixed
FL13239-R1 | Revision | YKK AP America | Shawn G. Collins, PE | Approved | Evaluation
History |  | Category: Windows | (813) 992-5195 |  | dry glazed (small Missile)
Subcategory: Fixed
FL13740-R1 | Revision | Energy Saving Window & Doors, Inc. | National Accreditation & Management Institute, | Approved * | NAMI
History |  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL13758-R1 | Revision | Windoor Incorporated | Steven M. Urich, PE | Approved | Evaluation
History |  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL14232-R1 | Revision | Peetz Windows and Doors, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
History |  | Category: Windows | (786) 315-2590
Subcategory: Fixed

## New Fixed Windows
Search Criteria |  | Refine Search
Code Version | 2007 | FL# | ALL
Application Type | New | Product Manufacturer | ALL
Category | Windows | Subcategory | Fixed
Application Status | Approved | Compliance Method | ALL
Quality Assurance Entity | ALL | Quality Assurance Entity Contract Expired | ALL
Product Model, Number or Name | ALL | Product Description | ALL
Approved for use in HVHZ | Yes | Approved for use outside HVHZ | Yes
Impact Resistant | Yes | Design Pressure | ALL
Other | ALL
FL10486 | New | Bonneville Windows and Doors | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL10506 | New | Diebold Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL10514 | New | Entreprises Doco | National Accreditation & Management Institute, | Approved | NAMI
|  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL10515 | New | Entreprises Doco | National Accreditation & Management Institute, | Approved | NAMI
|  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL10891 | New | Metra System | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL11008 | New | Entreprises Doco | National Accreditation & Management Institute, | Approved | NAMI
|  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL11074 | New | EFCO Corporation | Joel Grenstein, P.E. | Approved | Evaluation
|  | Category: Windows | (407) 629-8424
Subcategory: Fixed
FL11078 | New | T.M. Window and Door, LLC. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11204 | New | Force V Environmental, LLC | Ryan J. King, P.E. | Approved | Evaluation
|  | Category: Windows | (813) 787-8283
Subcategory: Fixed
FL11248 | New | Miami Wall Systems, Inc | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11477 | New | Regency Plus Incorporated | Rene J.Quiroga, PE | Approved | NAMI
|  | Category: Windows | (407) 681-6595
Subcategory: Fixed
FL11509 | New | Diebold Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11669 | New | Pittsburgh Corning Corporation | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11785 | New | Miami Wall Systems, Inc | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11786 | New | Miami Wall Systems, Inc | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11789 | New | Miami Wall Systems, Inc | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11790 | New | Miami Wall Systems, Inc | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL11993 | New | Windoor Incorporated | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL12038 | New | LAS Enterprises | National Accreditation & Management Institute, | Approved | NAMI
|  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL12043 | New | Hurd Windows and Doors, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12077 | New | Silverline Building Products Corp. | Ryan J. King, P.E. | Approved | Evaluation
|  | Category: Windows | (813) 787-8283
Subcategory: Fixed
FL12089 | New | Traco Windows and Doors, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12123 | New | Vistawall Architectural Products | Robert A. Walz, PE | Approved | NOA
|  | Category: Windows | (888) 262-9259
Subcategory: Fixed
FL12170 | New | Vistawall Architectural Products | Robert A. Walz, PE | Approved | NOA
|  | Category: Windows | (888) 262-9259
Subcategory: Fixed
FL12215 | New | YKK AP America | Manhar K Jadav, P.E. | Approved | Evaluation
|  | Category: Windows | (352) 589-1883
Subcategory: Fixed
FL12342 | New | Hope's Windows, Inc. | Ryan J. King, P.E. | Approved | Evaluation
|  | Category: Windows | (813) 787-8283
Subcategory: Fixed
FL12359 | New | Sun Metals Systems, Inc. | Ryan J. King, P.E. | Approved | Evaluation
|  | Category: Windows | (813) 787-8283 |  | dry glazed
Subcategory: Fixed
FL12388 | New | E.S. Windows, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12479 | New | Ultimate Door | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12497 | New | Loewen Windows | Window and Door Manufacturers Association | Approved | WDMA
|  | Category: Windows | (312) 673-4828
Subcategory: Fixed
FL12574 | New | Corrim Company | Jorge A. Pomerantz, P.E. | Approved | Evaluation
|  | Category: Windows | (954) 394-8521
Subcategory: Fixed
FL12609 | New | Diebold Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12630 | New | Arch Windows, LLC dba AWP | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12637 | New | EFCO Corporation | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Windows | (717) 676-5202
Subcategory: Fixed
FL12641 | New | Nan Ya Plastics Corporation USA | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12654 | New | Windoor Incorporated | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12693 | New | Zeluck Inc. | Steven M. Urich, PE | Approved | NOA
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL12697 | New | Traco Windows and Doors, Inc. | American Architectural Manufacturers Association | Approved | AAMA
|  | Category: Windows | (847) 303-5859 |  | NO QA Recommended for revocation
Subcategory: Fixed
FL12731 | New | CGI - Construction Glass Industries | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12733 | New | CGI - Construction Glass Industries | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12768 | New | Windoor Incorporated | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12774 | New | Arch Windows, LLC dba AWP | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12827 | New | PALM CITY MILLWORK, INC. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12828 | New | PALM CITY MILLWORK, INC. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12834 | New | Tischler und Sohn(USA)Limited | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12837 | New | Tischler und Sohn(USA)Limited | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL12857 | New | Surewood Door | Charles A. Pagen, P. E., Ph. D. | Approved | Evaluation
|  | Category: Windows | (941) 473-9331
Subcategory: Fixed
FL12872 | New | Traco Windows and Doors, Inc. | American Architectural Manufacturers Association | Approved | AAMA
|  | Category: Windows | (847) 303-5859
Subcategory: Fixed
FL12884 | New | NFP National Fenestration Product, Inc. | Sifu Zhou, P.E. | Approved | Evaluation
|  | Category: Windows | (305) 606-8257
Subcategory: Fixed
FL12913 | New | EFCO Corporation | Joshua M Royce, PE | Approved | Evaluation
|  | Category: Windows | (717) 676-5202
Subcategory: Fixed
FL13010 | New | Custom Window Systems Inc. | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13020 | New | The Hurricane Window and Door Factory | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13032 | New | Arch Windows, LLC dba AWP | National Accreditation & Management Institute, | Approved | NAMI
|  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL13045 | New | PGT Industries | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13072 | New | Fenestra America LLC. | Keystone Certifications, Inc. | Approved | Keystone
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13084 | New | Nan Ya Plastics Corporation USA | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL13105 | New | Loewen Windows | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455
Subcategory: Fixed
FL13128 | New | PALM CITY MILLWORK, INC. | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455
Subcategory: Fixed
FL13159 | New | St. Cloud Window, Inc. | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455
Subcategory: Fixed
FL13205 | New | Winco Window Company | Joseph A Reed, PE | Approved | Evaluation
|  | Category: Windows | (717) 764-7700
Subcategory: Fixed
FL13208 | New | Winco Window Company | Joseph A Reed, PE | Approved | Evaluation
|  | Category: Windows | (717) 764-7700
Subcategory: Fixed
FL13211 | New | Winco Window Company | Joseph A Reed, PE | Approved | Evaluation
|  | Category: Windows | (717) 764-7700
Subcategory: Fixed
FL13230 | New | Atrium Companies Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL13260 | New | Custom Window Systems Inc. | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13280 | New | KML Windows, Inc. | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13289 | New | Larson Manufacturing Company | William D. Robertson | Approved | Evaluation
|  | Category: Windows | (941) 764-9778
Subcategory: Fixed
FL13340 | New | Kawneer Company, Inc. | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455 |  | dry glazed
Subcategory: Fixed
FL13398 | New | Bonneville Windows and Doors | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13461 | New | Superior Window Corp. | National Accreditation & Management Institute, | Approved | NAMI
|  | Category: Windows | (804) 684-5124
Subcategory: Fixed
FL13484 | New | Loewen Windows | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455
Subcategory: Fixed
FL13514 | New | Regency Plus Incorporated | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL13526 | New | Winco Window Company | Joseph A Reed, PE | Approved | Evaluation
|  | Category: Windows | (717) 764-7700
Subcategory: Fixed
FL13535 | New | MADENA S.A. | Jesus Gonzalez, P.E. | Approved | Evaluation
|  | Category: Windows | (704) 827-1769
Subcategory: Fixed
FL13592 | New | EFCO Corporation | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13605 | New | Wausau Window and Wall Systems | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL13767 | New | EFCO Corporation | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13784 | New | EFCO Corporation | Rene J.Quiroga, PE | Approved | Evaluation
|  | Category: Windows | (407) 681-6595
Subcategory: Fixed
FL13865 | New | Eagle Window and Door, Inc | Steven M. Urich, PE | Approved | WDMA
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL13915 | New | E.S. Windows, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL13934 | New | Eurotech Industries, Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL13946 | New | Fleetwood Windows and Doors | American Architectural Manufacturers Association | Approved | AAMA
|  | Category: Windows | (847) 303-5859
Subcategory: Fixed
FL13952 | New | Superior Window Corp. | Xiaojun Gu | Approved | Evaluation
|  | Category: Windows | (305) 333-0157
Subcategory: Fixed
FL14015 | New | ProVia Door, Inc. | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL14091 | New | Wausau Window and Wall Systems | Christian Langley, PE | Approved | Evaluation
|  | Category: Windows | (954) 333-8965
Subcategory: Fixed
FL14136 | New | CGI - Construction Glass Industries | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL14148 | New | Hope's Windows, Inc. | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455
Subcategory: Fixed
FL14150 | New | Hope's Windows, Inc. | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455
Subcategory: Fixed
FL14151 | New | Hope's Windows, Inc. | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455
Subcategory: Fixed
FL14216 | New | YKK AP America | Shawn G. Collins, PE | Approved | Evaluation
|  | Category: Windows | (813) 992-5195
Subcategory: Fixed
FL14228 | New | Superior Window Corp. | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL14296 | New | CAOBA Doors | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed
FL14370 | New | Loewen Windows | Terrence E. Lunn, PE | Approved | Evaluation
|  | Category: Windows | (561) 625-6455
Subcategory: Fixed
FL14431 | New | Andersen Corporation | Steven M. Urich, PE | Approved | Evaluation
|  | Category: Windows | (717) 932-8500
Subcategory: Fixed
FL14492 | New | Sunshine Windows Manufacturing Inc. | Miami-Dade BCCO - VAL | Approved | NOA
|  | Category: Windows | (786) 315-2590
Subcategory: Fixed