**9thEdition (2026) FBC Code Update Development Tasks**

|  |  |
| --- | --- |
| **9th Edition (2026) Update to the Florida Building Code—** | |
| **Tasks** | **Schedule** |
| ***Selection of the model codes:*** |  |
| 2023 NEC published and available to the public; | Available |
| 2024 International Codes published and available to the public.  Note – 2024 IECC is not available yet – Projected availability April/May 2024. | Available |
| Commission selects available 2024 I Codes “model codes” (IBC, IMC, IPC, IFGC, IEBC) and 2023 NEC to conduct its review  2024 IECC | 2/13/2024  8/13/2024 |
| ***Review of the model code changes:*** |  |
| Staff post on Commission website/Building Code Information System (BCIS) analysis of the 2024 I-Code change to provide for identification of the following:  - Provisions which overlap with the provisions of the FBC  - Provisions which correlate directly with the provisions of the FBC  - Provisions which provide for energy efficiency standards that meet or  exceed the national energy standards mandated by Title III of the Energy  Conservation and Protection Act  - Provisions which are necessary to maintain eligibility for federal funding  and discounts from the National Flood Insurance Program, the Federal  Emergency management Agency, or the United States Department of  Housing and Urban Development  Staff post on the Commission website analysis of the 2024 IECC | 5/18/2024  *Completed*  July 27, 2024  Completed |
| Residential Construction Cost Impact Workgroup (RCCIWG) reviews the 2024 changes to the International Residential Code (IRC) and provides comments to the Commission’s TACs on impactful code changes.  RCCIWG meeting – Conference call/Webinar | 6/28/2024  Completed |
| 45 day public review and comment period ends ***(By Rule -45 day min before TAC review)***  2024 IECC - 45-day public review and comment period ends | 7/2/2024  Completed  9/9/2024 |
| Residential Construction Cost Impact Workgroup (RCCIWG) reviews the 2024 changes to the International Energy Conservation Code (IECC) – Residential Provisions and provides comments to the Commission’s Energy TAC on impactful code changes.  RCCIWG meeting – Conference call/Webinar | 8/20/2024  Completed |
| Staff post on Commission website analysis of the 2024 I-Code changes with public comments.  (Tracking Charts and code change monographs) | 8/2/2024  Completed |
| TACs review the 2024 changes to the I Codes and make recommendations to the Commission regarding those changes as follows:  That the Commission rejects certain model code provisions by consent agenda.    (Due to such issues as being unnecessary, negatively impacting the level of public  health, safety, or general welfare provided by an existing Florida Building Code  provision, diminishing the requirements of provisions related to wind resistance or  water intrusion, unnecessarily imposing additional costs, or potentially requiring  modification or further investigation before being adopted for use in this state)  That the Commission approves certain model code provisions by consent agenda.  (When considering whether to recommend inclusion on a consent agenda for  approval, the TACs shall consider such criteria as whether the model code  provisions are editorial or organizational in nature, correct an error, provide  clarification, provide for alternative design methods, improve the effectiveness of  the code, are uncontroversial to affected stakeholders, or are required by law.)  That the Commission approve or reject certain model code provisions after considering them individually  (When recommending individual consideration of model code updates, the TACs  shall consider such criteria as whether the update has the potential to impose  significant costs, cause confusion or regulatory difficulty, may be unnecessary, is  highly controversial to affected stakeholders, or requires further evaluation.)  TACs meetings – See schedule | 9/12-20/2024  Completed |
| Staff post TACs’ recommendations online for further public review | 10/8/2024  Completed |
| Deadline for requesting amendments (2024 I-Codes changes) to be pulled of the consent agenda for individual consideration | 11/19/2024  Completed |
| Commission considers TACs’ recommendations regarding the latest changes to the model codes - on site meeting (TBD) | 12/10-11/2024  Completed |
| Staff post Commission’s recommendations online | 1/3/2025  Completed |
| ***Proposed modification to the foundation code and Commission’s approved I –Codes changes*** |  |
| Period for the public to propose modifications to the 8th Edition (2023) FBC and the Commission’s approved I-Codes changes  Send memo to local governments regarding local amendments | **1/3/2025 – 2/17/2025**  Completed |
| Proposed amendments reviewed by staff and posted to the Commission website | **3/3/2025**  Completed |
| 1st 45 day comment period ends ***(By law -45 day min before TAC review)*** | **4/16/2025**  Completed |
| Staff post on Commission website proposed code changes (Tracking Charts and Detail Reports) and local amendments to the base code | **5/2/2025**  Completed |
| TACs consider proposed modifications (1st 45 day comment period)  TACs meetings – 2-days of virtual meetings and 5-days of on-site meetings | 6/16-6/17 and 6/23-6/27/2025  Completed |
| TACs recommendations posted to the website Starting date for the 2nd 45 day comment period | **7/11/2025** |
| Residential Construction Cost Impact Workgroup (RCCIWG) reviews the TACs’ recommendations with regard to the proposed modifications to the Florida Residential Code (FRC) and provides comments to the TACs/Commission on impactful code changes.  RCCIWG meeting – Conference call/Webinar meeting (TBD) | **8/15/2025** |
| 2nd 45 day comment period ends ***(by law – 45 day min before Commission review)*** | **8/~~25~~ 24/2025** |
| Staff post on Commission website proposed code changes with comments (Tracking Chats and Details Reports) | **9/19/2025** |
| TACs consider public comments on their actions on the proposed mods  TACs meetings – 4-day meetings [2-day on-site (TBD) and 2 – day via conference/webinar] – As needed and as applicable | **10/6-10/2025** |
| Staff post on Commission website TACs consideration of public comments | **11/6/2025** |
| Deadline for requesting amendments to be pulled of the consent agenda for individual consideration | **11/17/2025** |
| Commission considers TAC recommendations (2nd 45-day comment period)  Commission – 2-day meeting | **12/9-10/2025** |
| 9th Edition (2026) FBC (8th Edition (2023) FBC, Florida Supplement and Commission’s approved I Codes) posted online | **12/22/2025** |
| ***Provide Supplements to ICC for integration into the 9th Edition (2026) FBC*** |  |
| TACs review comments to Rule Development Workshop of …..and make recommendations to the Commission  TACs meetings - 3-day on-site meetings and 3-day conference call/webinar meetings | TBD |
| **Rule development Workshop**  Commission – 1-day meeting | TBD |
| TACs review comments to Rule Development Workshop of ……and make recommendations to the Commission  TACs meetings - 2-day conference call/webinar meetings | TBD |
| **Rule development Workshops**  Commission – 1-day meeting | TBD |
| Integrated Draft 9th Edition (2026) FBC – Posted online | TBD |
| ***Hearing*** on 9th Edition (2026) FBC to consider received comments | TBD |
| ***Final Rule Hearing*** on 9th Edition (2026) FBC/Commission approves final version of Code  9th Edition (2026) Florida Fire Prevention Code available in final format | TBD |
| Rule Submitted to Secretary of State and Supplement/Integrated posted online – subject to addressing all JAPC’s concerns | TBD |
| Final FBC -PDF posted | TBD |
| Printed Code available - subject to negotiation with ICC | TBD |
| 2026 FBC **(9th edition)** effective date (6 – months after publication) | 12/31/2026 |
|  |  |
| 553.73(7)(e) A rule updating the Florida Building Code in accordance with this subsection shall take effect no sooner than 6 months after publication of the updated code. Any amendment to the Florida Building Code which is adopted upon a finding by the commission that the amendment is necessary to protect the public from immediate threat of harm takes effect immediately. | |